## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1815456 | Zixuan Li | Week starting: | 2025-03-31
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-03-31 | 19:00 | 20:00 | 1 | Group Meeting | Ensures cohesive team effort and clarity on upcoming deliverables(business case). | Prioritized document updates and assigned roles for data handling.
Tuesday | 2025-04-01 | 13:00 | 14:00 | 1 | Meet with client. | Facilitates timely feedback for accurate data functionality. | Collected suggestions and noted data handling expectations.
Wednesday | 2025-04-02 | 11:00 | 13:30 | 3 | Researched FastAPI | uilds technical foundation for implementing backend services and APIs. | Understood API structure and explored documentation.
Thursday | 2025-04-03 | 11:00 | 12:00 | 1 | Attend Lecture | Enhances ability to anticipate and manage uncertainties in project work. | Gained actionable methods to reduce potential development risks.
|  | 13:00 | 18:00 | 5 | Researched business case structure, key components, and assessment criteria. | Helps ensure our proposal aligns with academic expectations and real-world standards. | Took notes on successful formats and evaluation rubrics. Next: apply to improve our business case.
|  | 18:00 | 21:00 | 3 | Updated prototype by adding “Contact Us” and “User Watch List” pages with linked navigation with Weian. | Enhances user experience by enabling feedback, personalization, and better platform interaction. | Completed layout and integrated both pages into main user flow. Next: polish design and test usability.
Friday | 2025-04-04 | 14:00 | 18:00 | 4 | Drafted the first section of the business case(the whole part one) | Provides a foundation for the case | Completed first draft of Part 1. Next: peer review and refinement.
|  | 19:00 | 20:00 | 1 | Group Meeting | Ensures team is aligned before entering the next sprint cycle. | Confirmed task responsibilities and created updated sprint outline.
Saturday | 2025-04-05 | 12:00 | 20:00 | 8 | Revised Part 1 based on peer feedback and expanded business justification. | Strengthens argument clarity and aligns content with marking rubric. | Improved logic and coherence.
Sunday | 2025-04-06 | 18:00 | 21:00 | 3 | Finalized formatting and added missing supporting details to the business case. | Ensures the document is polished and complete for submission. | Final version ready. Next: check everything is fine.
|  |  | Total | 30