## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1815441 | Weian Liu | Week starting: | 2025-03-17
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-03-17 | 5:00 | 20:00 | 3 | Organize and lead team meeting | Discussion on User Stories,Prototype and Client Discussion Preparation | Ask Dr.Li's opinion, prepare questions. Prepare for the next meeting on Friday
|  | 12:00 | 14:00 | 2 | Organize the content of the meeting | Set foundation for project tools and structure of sprint tasks | Update prototype, finalize user stories, prep for client confirmation on tech stack
Tuesday | 2025-03-18 | 12:00 | 15:00 | 3 | Preparation of client meeting content, organized into a pdf. Participated client meeting with Dr. Li. | Clarifies product direction before starting key development and sprint planning | Awaiting client opinions on Superbase, AI usage, and framework approval
|  | 15:00 | 17:00 | 2 | Organize content for client meetings. Plan and assign tasks according to client's requirements. | Established sprint priorities, UI requirements, and prototype improvements | Update presentation, confirm environment setup, share GitHub with client, improve UI
Wednesday | 2025-03-19 | 12:00 | 17:00 | 5 | Adjusting as well as shining user stories with Zixuan | Serves as the roadmap for frontend, backend, search, login, watchlist, and AI features | Use stories to guide task assignment, sprint timing, and project milestones
Thursday | 2025-03-20 | 12:00 | 4:00 | 4 | Searching for information to create a pitch presentation slide show with Zixuan | Helped us gather useful examples and inspiration for slide content and structure | Collected reference slides, decided on rough structure and visual direction
|  | 19:00 | 20:00 | 1 | Preparing for Friday's group meeting | Prepares team for finalizing pitch presentation and aligning task assignments | Finalize draft slides and delegate responsibilities for the weekend
Friday | 2025-03-21 | 11:00 | 13:00 | 2 | Attended lecture. | Focused on project management. | Methods about project management.
|  | 13:00 | 14:00 | 1 | Team meeting. | Reviewed project scope and divided upcoming tasks. | Defined next steps for API research and technology selection.
|  | 15:00 | 17:00 | 2 | Organize the content of the meeting | Tightened focus on setting up development base and aligning pitch strategy | Share final user story version, add “future plans” section, build slide visuals, and submit timesheets
Saturday | 2025-03-22 | 11:00 | 15:00 | 4 | Creating pitch presentation | It helped us clarify the problem we’re solving, what makes our solution special, and how we plan to build it (tools, timeline, risks, etc.). | incorporate feedback after the pitch session
|  | 19:00 | 22:00 | 3 | Creating pitch presentation
|  |  | Total | 32