## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1900315 | Emmanuel Philipose Antony | Week starting: | 2025-04-07
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-04-07 | 17:00 | 19:30 | 2.5 | Prepare group meeting 1 agenda | As per schedule the meeting secretary of the week needs to prepare meeting 1 agenda | The meeting agenda was prepared with items to elicit for the coming week. Document shared with team and was uploaded to document repository.
|  | 19:30 | 20:30 | 1 | Weekly Team meeting 1 | The meeting was to discuss tasks for this week and prepare for upcoming client meeting | The items for this week was discussed and split. Furthermore, the Q and A session was reminded for next client meeting.
|  | 20:30 | 23:00 | 2.5 | Prepare client meeting agenda | As per schedule the meeting secretary of the week needs to prepare client meeting agenda | The meeting agenda was prepared with items to elicit for demonstrating progress and queries to client. Document shared with team and was uploaded to document repository.
Tuesday | 2025-04-08 | 13:00 | 14:00 | 1 | Weekly Client Meeting with Dr.Li | This meeting was conducted to demonstrate development progress with the client and for Q and A session for the pitch presentation | Client provided valuable feedback on development progress and had a good Q and A session. The client also stressed on continuing development throughout mid semester break.
|  | 20:00 | 23:30 | 3.5 | Prepare Client meeting minutes | As per schedule the meeting secretary of the week needs to prepare client meeting minutes | The client meeting minutes were prepared including all items discussed during the meeting and was uploaded to the document repository.
Wednesday | 2025-04-09 | 18:00 | 21:30 | 3.5 | Prepare group meeting 1 minutes | As per schedule the meeting secretary of the week needs to prepare meeting 1 minutes | The group meeting 1 minutes were prepared including all items discussed during the meeting and was uploaded to the document repository.
Thursday | 2025-04-10 | 14:30 | 20:00 | 5.5 | Research on Tailwind CSS | Tailwind CSS is required for unifying the styling package for the project's front-end | Tailwind CSS turned out to be more resielient than emotion package used by Material UI components. Need to work on unifying all styling code to Tailwind.
Friday | 2025-04-11 | 16:00 | 18:30 | 2.5 | Prepare group meeting 2 agenda | As per schedule the meeting secretary of the week needs to prepare meeting 2 agenda | The meeting agenda was prepared with items to elicit for the coming weekend and mid semester break. Document shared with team and was uploaded to document repository.
|  | 19:00 | 20:00 | 1 | Weekly Team meeting 2 | Discussed progress on tasks assigned and also discussed parts to be completed during weekend | Progress on tasks were demonstrated and discussed. The schedule for the upcoming mid semester break was finalised.
|  | 20:30 | 22:30 | 2 | Review this week's lecture online | This lecture focused on the understanding of user interfaces | This lecture helped understand the importance of UX and standards to be maintained during development.
Saturday | 2025-04-12 | 10:00 | 13:00 | 2 | Inspect github board for resilience of Project Management | This is required for ensuring the board is ready for W2-W6 evaluation | The requirement for changes were highlighted to the team members and ensured that all documents are in order.
|  | 15:00 | 18:30 | 3.5 | Prepare group meeting 2 minutes | As per schedule the meeting secretary of the week needs to prepare meeting 2 minutes | The group meeting 2 minutes were prepared including all items discussed during the meeting and was uploaded to the document repository.
|  |  | Total | 30.5