## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1917266 | Daming Chen | Week starting: | 2025-03-10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-03-10 | 13:00 | 15:00 | 2 | Participated in the first team meeting and familiarized with project requirements. | Established initial project communication. | Understood project requirements. Decided to rotate meeting documentation responsibilities.
Tuesday | 2025-03-11 | 13:00 | 16:00 | 3 | Learned Git and GitHub basics. | Essential for managing project versions and collaboration. | Familiarized with project structure and task division. Next: Collaborate on repository branch setup.
Wednesday | 2025-03-12 | 18:00 | 20:00 | 2 | Researched similar movie recommendation platforms (e.g., IMDb, Letterboxd). | Provided design inspiration and UX/UI reference for our interface. | Analyzed layout patterns and user flows. Next: Summarize key findings to guide our wireframe design.
Thursday | 2025-03-13 | 14:00 | 16:00 | 2 | Attended workshop and review the pitch presentation requirements. | Ensures alignment with assessment standards and improves project pitching strategy. | Learned structure, storytelling techniques, and slide design best practices.
Friday | 2025-03-14 | 11:00 | 13:00 | 2 | Attended lecture. | Focused on the pitch presentation requirements. | Mastered key elements.
|  | 19:00 | 20:00 | 1 | Team meeting. | Discuss topics covered in lecture and initially assign tasks | Defined next steps for AI research and technology selection.
Saturday | 2025-03-15 | 0:00 | 12:00 | 12 | Designed homepage and signup page prototypes using Figma. | Provides visual foundation for front-end development and user flow validation. | Created interactive wireframes with core UI components. Next: Conduct team review and refine based on feedback.
Sunday | 2025-03-16 | 19:00 | 22:00 | 3 | Casual team meeting. | Focused on project management and user stories. | Gathered feedback on homepage and signup page. Defined key User Stories and development management.
|  |  | Total | 27