## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1917266 | Daming Chen | Week starting: | 2025-03-31
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-03-31 | 18:00 | 21:00 | 3 | Hosted team meeting and prepared agenda/minutes. | Weekly progress review and clarity on upcoming deliverables. | Next: Prepare for Business Case.
Tuesday | 2025-04-01 | 13:00 | 15:00 | 2 | Participated Client Meeting. | Project progress review with client | Gathered client feedback and documented minutes of meeting.
Wednesday | 2025-04-02 | 14:00 | 17:00 | 3 | Reviewed Business Case assessment criteria. | Establishes foundational standards for aligning with client/industry expectations. | Next: Draft initial version based on research insights.
Friday | 2025-04-04 | 11:00 | 12:00 | 1 | Attend Lecture. | Clarify Business Case requirments. | Gained knowledge of project management.
|  | 18:00 | 21:00 | 3 | Hosted team meeting and prepared agenda/minutes. | Weekly summary and next sprint planning | Clarified task responsibilities for Business Case.
Saturday | 2025-04-05 | 13:00 | 17:00 | 4 | Drafted Part 2 Team Organization & Communication Plan sections of Business Case | Critical for validating project alignment with industry demand. | Next: Refine content and integrate team feedback.
|  | 17:00 | 18:00 | 1 | Conducted milestone review and Gantt chart alignment session. | Synchronizes team deliverables with project timelines and resource capacity.
|  | 20:00 | 12:00 | 4 | Finalized own part of Business Case document and standardized formatting. | Ensures professional deliverable compliance with client's guidelines. | Next: Code development.
|  |  | Total | 21