## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1900315 | Emmanuel Philipose Antony | Week starting: | 2025-05-12
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-05-12 | 16:30 | 19:00 | 2.5 | Prepare group meeting 1 agenda | As per schedule the meeting secretary of the week needs to prepare meeting 1 agenda | The meeting agenda was prepared with items to elicit for the coming week. Document shared with team and was uploaded to document repository.
|  | 19:00 | 20:00 | 1 | Weekly Team meeting 1 | The meeting was to discuss tasks for this week and prepare for upcoming client meeting. | The items for this week was discussed and split. Questions raised by team members to be asked in the next client meeting.
Tuesday | 2025-05-13 | 17:30 | 21:00 | 3.5 | Prepare group meeting 1 minutes | As per schedule the meeting secretary of the week needs to prepare meeting 1 minutes | The group meeting 1 minutes were prepared including all items discussed during the meeting and was uploaded to the document repository.
Wednesday | 2025-05-14 | 17:00 | 19:00 | 2 | Work on User Profile Page enhancements suggested by teammates during group meeting 1 | This is for making sure that the design of user profile page is favourable to a user in terms of viewing and usability. | The updates were completed and is ready for presenting to the client.
|  | 19:30 | 22:00 | 2.5 | Prepare client meeting agenda | As per schedule the meeting secretary of the week needs to prepare client meeting agenda | The meeting agenda was prepared with items to elicit for demonstrating progress and queries to client. Document shared with team via teams chat and was uploaded to document repository.
Thursday | 2025-05-15 | 13:00 | 14:00 | 1 | Weekly Client Meeting with Dr.Li | This meeting was conducted to demonstrate development progress with the client and gather feedback for all the UI/UX components created so that integration could be done smoothly. | Client provided valuable feedback on development progress and suggested UI/UX improvements.
|  | 18:30 | 22:00 | 3.5 | Prepare Client meeting minutes | As per schedule the meeting secretary of the week needs to prepare client meeting minutes | The client meeting minutes were prepared including all items discussed during the meeting and was uploaded to the document repository.
Friday | 2025-05-16 | 15:00 | 17:30 | 2.5 | Prepare group meeting 2 agenda | As per schedule the meeting secretary of the week needs to prepare meeting 2 agenda | The meeting agenda was prepared with items to elicit for the coming weekend. Document shared with team and was uploaded to document repository.
|  | 19:00 | 20:00 | 1 | Weekly Team meeting 2 | Discussed progress on tasks assigned and also discussed parts to be completed during weekend. | Progress on tasks were demonstrated and discussed. Tasks for weekend needs to be worked on.
Saturday | 2025-05-17 | 11:00 | 13:00 | 2 | Inspect github board for resilience of Project Management | This is required for ensuring the board is in line for W7-W12 evaluation | The requirement for changes were highlighted to the team members via teams chat and ensured that all documents are in order.
|  | 15:00 | 18:30 | 3.5 | Prepare group meeting 2 minutes | As per schedule the meeting secretary of the week needs to prepare meeting 2 minutes | The group meeting 2 minutes were prepared including all items discussed during the meeting and was uploaded to the document repository.
Sunday | 18/5/2025 | 12:30 | 18:00 | 5.5 | Work on UI/UX improvements suggested by Dr.Li in the client meeting | This work is to ensure that the components for project pages are in line with the client's requirements ready for integration | The components are ready in line with client feedback and is ready for integration.
|  |  | Total | 30.5