## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1815441 | Weian Liu | Week starting: | 2025-05-26
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-05-26 | 9:30 | 13:30 | 4 | Continued work on completing the testing plan | Finalized all remaining black-box tests for this iteration | Test document completed and logged; ready to move to presentation tasks
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly task review and coordination of remaining deliverables | Updated task assignments for report and presentation work
Thursday | 2025-05-29 | 13:00 | 14:00 | 1 | Attended client meeting | Got final review points on layout flow, avatar design, and mobile responsiveness | Adjustments needed for profile section and visual consistency
|  | 14:00 | 20:00 | 6 | Drafted first version of presentation slides and listed current missing content | Start of final deliverable prep; ensures coverage of all criteria | First version ready for group review tomorrow
Friday | 2025-05-30 | 9:30 | 12:30 | 3 | 设计第一版presentation 列出目前欠缺的东西 | Helps check completeness and avoid last-minute content gaps | Identified missing visuals and API-related slides
|  | 11:00 | 12:00 | 1 | Attend Lecture | Understand demo and report | Improved understanding of delivery standards
|  | 13:30 | 17:30 | 4 | Edited presentation content; added context and UI background for clarity | Improved narrative flow and design detail coverage | Added visual cues and explanations for hidden features
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly summary and next plan | Next tasks assigned
Satureday | 2025-05-31 | 8:00 | 15:00 | 7 | Discussed and redesigned presentation structure with teammates; ensured evaluation criteria are fully addressed | Fine-tuned flow and visual layout before recording | Draft refined and prepped for final polish
Sunday | 2025-06-01 | 15:00 | 20:00 | 5 | Finalized presentation version | matches all assessment requirements | Version locked
|  |  | Total | 33