## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1815441 | Weian Liu | Week starting: | 2025-04-28
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-04-28 | 10:30 | 14:30 | 4 | Learning implementation of User Session Management. | Needed for building secure login/logout features for our users | Understood session tokens and login flow; will start coding on Tuesday
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly task review and progress alignment | Updated task assignments
Tuesday | 2025-04-29 | 14:00 | 22:00 | 8 | Initial implementation of User Session Management. | Core feature to handle user authentication and session control | Login/logout working in dev mode; needs token error handling and cleanup
Wednesday | 2025-04-30 | 9:00 | 18:00 | 9 | study about testing plan | Helps ensure we can test features like login | Took notes on test case structure; will apply to login and chat functions
Thursday | 2025-05-01 | 13:30 | 17:30 | 4 | Attended client meeting; documented feedback; reviewed technical priorities | Aligns project direction with stakeholder expectations; confirmed chatbot and UI direction | Feedback translated into updated dev plan; prioritize search page and UI polishing
Friday | 2025-05-02 | 9:30 | 16:30 | 7 | learning UI, help frontend | Helped improve user experience on key pages | Updated UI styles, fixed spacing issues, added responsive layout
|  | 11:00 | 12:00 | 1 | Attend Lecture | Understand Testing Plan | Improved understanding of delivery standards
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly summary and next sprint planning | Next tasks assigned
|  |  | Total | 35