## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1815441 | Weian Liu | Week starting: | 2025-05-05
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-05-05 | 8:00 | 18:00 | 10 | finished 4 test case,test contest,test movies, test out service, movie service | End-to-end testing to verify system logic and features | Found many issues in test results; need to fix code
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly task review and progress alignment | Updated task assignments
Tuesday | 2025-05-06 | 9:00 | 5:00 | 8 | Debugged errors, checked code logic, and continued testing | Helps ensure stable functionality before we move to final report | Fixed part of the code; more testing still needed
Wednesday | 2025-05-07 | 13:00 | 16:00 | 3 | Wrote test plan based on project requirements | Needed for structuring testing phase and making report clear | Drafted test plan outline and sample cases
Thursday | 2025-05-08 | 12:00 | 16:00 | 4 | Attended client meeting; collected feedback on sorting, login UI, chatbot confirmation | Client validation of current system; redirected design priorities | Feedback logged; prepared to discuss in internal group meeting
Friday | 2025-05-09 | 9:30 | 15:30 | 6 | Completed milestone report | Final step of this iteration for team submission | Reviewed with group and ready to submit by weekend
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly summary and next sprint planning | Next tasks assigned
|  |  | Total | 33