## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1815441 | Weian Liu | Week starting: | 2025-05-12
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-05-12 | 9:30 | 12:30 | 3 | Updated the test plan design based on teammates' latest feedback | Helped adjust testing scope for the newest version of the system | Ready to build detailed test cases this week
|  | 19:00 | 20:00 | 1 | Group Meeting | Checked progress and re-arranged weekly responsibilities | Task list updated for each member
Wednesday | 2025-05-14 | 10:30 | 12:30 | 2 | Re-edited test plan based on uploaded final prototype version | Ensures the test plan aligns with updated UI flow and logic | Final sections of test plan drafted, review scheduled
|  | 14:00 | 18:00 | 4 | Found existing issues with test cases, discussed with team | Identified flaws early in testing scope, avoids future confusion | Meeting scheduled for tomorrow to finalize corrections
Thursday | 2025-05-15 | 13:00 | 14:00 | 1 | Attended client meeting | Collected client’s input on interface flow and login functionality | Feedback logged for internal refinement
|  | 14:00 | 20:00 | 6 | Adjusted the test plan to match black-box testing standards and added user-oriented flows | Upgraded the test coverage to match expected release behavior | Test plan now includes user walkthroughs and full case logic
Friday | 2025-05-16 | 10:30 | 13:30 | 3 | Finalized full test plan structure | Prepares for the next QA milestone | Ready for export and team review
|  | 15:30 | 18:30 | 3 | Completed polishing and versioning of test plan | Keeps testing files organized for submission | Final files ready to be shared
|  | 19:00 | 20:00 | 1 | Group Meeting | Closed out the week and assigned final adjustments | Agreed on next testing actions
Sunday | 2025-05-18 | 10:00 | 18:00 | 8 | Reviewed the entire test plan with Zixuan, applied edits, and structured export | Ensures accuracy before submission and syncing across team members | Shared test plan and Excel with team for record keeping
|  |  | Total | 32