## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1900315 | Emmanuel Philipose Antony | Week starting: | 2025-06-02
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-06-02 | 19:00 | 20:00 | 1 | Weekly Team meeting 1 | The meeting was to discuss tasks for this week and record questions to client in the upcoming final team meeting. | Need to work on tasks assigned for this week.
Tuesday | 2025-06-03 | 13:30 | 16:30 | 3 | Create plans for resolving bugs reported while testing | This is essential to resolve the bugs identified during testing. | Plans formulated for resolving bugs. Have to apply steps to resolve bugs
|  | 18:00 | 23:00 | 5 | Apply UI/UX suggestions provided by client | The project needs to be aligned with client's interests if the bandwidth allows to do so. | Enhancements applied. To be presented to the client in the final team meeting.
Wednesday | 2025-06-04 | 17:30 | 22:00 | 4.5 | Fix Bug: Handle use case of video buttons for trailer and teaser to be hidden and corresponding message displayed if either or both don't exist in database | The video buttons should not be available in case there is either of trailer/teaser or both isn't available | Bug handled and pushed to ErrorHandle Branch for teammates to test.
Thursday | 2025-06-05 | 14:30 | 18:00 | 3.5 | Fix Bug: Handle use case of movie having no reviews and an encouraging message to post one is provided to the user. | The user must be informed of a case where no one has reviewed a movie in place of an empty review scroll component, possibly encouraged to post one as well. | Bug handled and pushed to ErrorHandle Branch for teammates to test.
Friday | 2025-06-06 | 13:00 | 14:00 | 1 | Weekly Client Meeting with Dr.Li | This meeting was to demostrate the project progress and discuss Demo Presentation. | Dr. Li provided valuable advise pertaining to Demo presentation, things to keep in mind and suggestions to do it better.
|  | 14:00 | 15:00 | 1 | Weekly Team meeting 2 | Discussed progress on tasks assigned and also discussed parts to be completed during weekend. | Need to work on items to resolve bug in assigned in the front-end space.
|  | 18:00 | 22:30 | 4.5 | Fix Bug: Handle use case of unauthenticated user to add movie to watchlist and post review | An unathenticated user should be directed to login to access the full capability of the Lumiere system | Bug handled and pushed to ErrorHandle Branch for teammates to test.
Saturday | 2025-06-07 | 17:00 | 19:00 | 2 | Review this week's lecture | The lecture was based on the final demo presentation. | Learned about the things to keep in mind for creating final presentation. Need to apply learnings while presenting.
Sunday | 2025-06-08 | 19:00 | 20:00 | 1 | Final presentation planning meeting | This meeting is to discuss the plan for the final demo presentation, to fix parts to be handled by each team member and to fix a time for rehearsal. | Have to learn and practice presenting the part for demo presentation.
|  | 20:00 | 12:00 | 4 | Final presentation part learn and personally rehearse | This meeting is to discuss the plan for the final demo presentation, to fix parts to be handled by each team member and to fix a time for rehearsal. | Learned and practiced presenting the part for demo presentation. Have to attend rehearsal at University in a booked meeting room with Teammates.
|  |  | Total | 30.5