## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1900315 | Emmanuel Philipose Antony | Week starting: | 2025-05-19
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-05-19 | 19:00 | 20:00 | 1 | Weekly Team meeting 1 | The meeting was to discuss tasks for this week, discuss Testing Plan submission, and record questions to client in the upcoming team meeting. | Testing Plan requirements were discussed. Need to work on tasks assigned for this week.
Tuesday | 2025-05-20 | 12:45 | 17:45 | 5 | Learn about integrating Next JS with FastAPI and specifically POST routes | This learning is crucial for integrating the front-end and back-end parts of the project. | Gained knowledge on how to create Server Actions in front end to interact with routes in backend.
|  | 20:00 | 23:00 | 3 | Try GET and POST routes created by Back-end engineer in FastAPI | This is required for identifying how APIs in FastAPI behave for integration. | Learned how different APIs behave in FastAPI using Swagger UI
Wednesday | 2025-05-21 | 17:30 | 22:00 | 4.5 | Record the API routes required for handling viewing of reviews and posting reviews from the Movie Description page. | This is crucial for understanding which all API routes needs to be utilised for displaying all reviews of a movie and to post reviews from the Movie Description page. | Recorded API routes are required completing backend integration with Movie Description page. These are to be utilised to create Server Actions to interact with the APIs.
Thursday | 2025-05-22 | 13:00 | 14:00 | 1 | Weekly Client Meeting with Dr.Li | This meeting was to demostrate the project progress and discuss Testing Plan assignment. | Dr. Li provided valuable advise pertaining to Testing Plan creation and how to structure it.
|  | 16:00 | 21:00 | 5 | Create Server Actions for populating reviews and to handle the review post function of review dialog box in Movie Description page. | Server Actions are required for live data population of the reviews in Movie Details page pertaining to each movie and to enable posting of reviews. | Server Actions for different parts/components of Movie Details page ready for integration.
Friday | 2025-05-23 | 12:00 | 17:00 | 5 | Integrate the Movie Details page with the Server Actions created for Reviews - populating and posting. | This is required for components specific to reviews interact with Back-End routes for live data population of the reviews in Movie Details page pertaining to each movie and to enable posting of reviews. | Movie details components pertaining to reviews fully integrated to handle viewing and posting of reviews.
|  | 19:00 | 20:00 | 1 | Weekly Team meeting 2 | Discussed progress on tasks assigned, Testing Plan submission and also discussed parts to be completed during weekend such as parts in front-end and back-end. | Need to work on items assigned in the front-end space.
Saturday | 2025-05-24 | 11:00 | 13:30 | 2.5 | Test the integration of Reviews - viewing all reviews and posting reviews | This is to ensure the proper working of review viewing and posting via Movie Description page. | Components integrated pertaining to Reviews in Movie Description page is working as expected.
|  | 14:45 | 16:15 | 1.5 | Create a branch with source as development and push the new changes so that it can be safely merged | This is to ensure that project development branch doesn’t get corrupted | New branch created and changes pushed.
|  | 17:00 | 19:00 | 2 | Review this week's lecture | The lecture was based ethical part of project development and finally advices for testing plan submission. | Learned about the importance of ethics in software development.
|  |  | Total | 31.5