## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1900315 | Emmanuel Philipose Antony | Week starting: | 2025-05-26
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-05-26 | 19:00 | 20:00 | 1 | Weekly Team meeting 1 | The meeting was to discuss tasks for this week and record questions to client in the upcoming team meeting. | Need to work on tasks assigned for this week.
Tuesday | 2025-05-27 | 12:00 | 16:30 | 4.5 | Record the API routes required for handling viewing of watchlist movies and adding to watchlist. | This is crucial for understanding which all API routes needs to be utilised for displaying all watchlist movies of a user and to add/delete movies to/from watchlist. | Recorded API routes are required completing backend integration for watchlists. These are to be utilised to create Server Actions to interact with the APIs.
|  | 17:00 | 23:00 | 6 | Create Server Actions for fetching watchlist, adding and deleting movies from watchlist. | Server Actions are required for live data population of the movies in Watchlist page and to enable add/delete movies to/from watchlist. | Server Actions for different parts/components handling viewing, add/delete movies to/from watchlist ready for integration.
Wednesday | 2025-05-28 | 17:30 | 23:30 | 6 | Integrate the Watchlist page with the Server Actions created for populating a logged in user's Watchlist and new bookmark component to handle add/delete movies to/from watchlist. | This is required for the integration of the back-end with front-end to handle the Watchlist capability of the project. | Watchlist capability, i.e, watchlist viewing, add/delete movies to/from watchlist fully integrated.
Thursday | 2025-05-29 | 13:00 | 15:00 | 2 | Implement functioning of search and filters for watchlist page | This is to ensure the proper working of filter and search in Watchlist page. | Components pertaining to filter and search in Watchlist page is working as expected.
|  | 16:00 | 17:30 | 1.5 | Create a watchlist carousel component to display watchlist movies in homepage. | This is to enhance the watchlist usability in the homepage for a logged in user. | Watchlist carousel capability created for Homepage.
|  | 18:30 | 21:00 | 2.5 | Integrate Watchlist Carousel component | This is to integrate the watchlist carousel component with one of the server actions to populate watchlist movies of logged in user. | Watchlist carousel capability fully integrated for Homepage.
Friday | 2025-05-30 | 8:30 | 11:00 | 2.5 | Test the integration of Reviews - viewing all reviews and posting reviews | This is to ensure the proper working of review viewing and posting via Movie Description page. | Components integrated pertaining to Reviews in Movie Description page is working as expected.
|  | 11:00 | 12:30 | 1.5 | Create a branch with source as development and push the new changes so that it can be safely merged | This is to ensure that project development branch doesn’t get corrupted | New branch created and changes pushed.
|  | 13:00 | 14:00 | 1 | Weekly Client Meeting with Dr.Li | This meeting was to demostrate the project progress and discuss Testing Plan results. | Dr. Li provided valuable advise pertaining to bugs and how to resolve them. Also provided few UI/UX suggestions to improve usability.
|  | 14:00 | 15:00 | 1 | Weekly Team meeting 2 | Discussed progress on tasks assigned and also discussed parts to be completed during weekend such as parts in front-end and back-end. | Need to work on items assigned in the front-end space.
Saturday | 2025-05-31 | 11:00 | 13:30 | 2.5 | Review Bug Log | Bug log is the record of issues encountered during testing. | This logs needs to be utilised for planning bug resolution of the project.
|  | 17:00 | 19:00 | 2 | Review this week's lecture | The lecture was based on the final report creation. | Learned about the things to keep in mind for creating final report. Need to apply learnings while writing final report.
|  |  | Total | 34