## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1900315 | Emmanuel Philipose Antony | Week starting: | 2025-04-28
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-04-28 | 19:00 | 20:00 | 1 | Weekly Team meeting 1 | The meeting was to discuss tasks for this week and discuss plans for W7-W12 to be presented to client in the upcoming team meeting. | Tasks to accomplish in the next 6 weeks, i.e, W7-W12 were discussed by team members. Also need to work on tasks assigned for this week.
Tuesday | 2025-04-29 | 19:30 | 22:30 | 3 | Learn Shadcn UI - Part 1 | Shadcn UI components required for making user friendly UI for users (consistent Tailwind CSS). | Learned the ability of Shadcn UI components to make user friendly UI for users. This was decided as per decision to go with unified CSS which was Tailwind.
Wednesday | 2025-04-20 | 19:00 | 23:00 | 4 | Learn Shadcn UI - Part 2 | Shadcn UI components required for making user friendly UI for users (consistent Tailwind CSS). | Learned the ability of Shadcn UI components to make user friendly UI for users. This was decided as per decision to go with unified CSS which was Tailwind.
Thursday | 2025-05-01 | 13:00 | 14:00 | 1 | Weekly Client Meeting with Dr.Li | This meeting was to discuss the upcoming weeks in Milestone 2 and the split of tasks in upcoming weeks to stay on target. | Dr. Li provided advice to be alert of the timelines available for the components creation and be ready for integration.
|  | 16:00 | 20:00 | 4 | Create Watchlist front-end capability with placeholders | Required part of the project pages. | The placeholders needs to be replaced with live data in the weeks of integration efforts to handle watchlist information.
Friday | 2025-05-02 | 12:00 | 18:00 | 6 | Implement Movie Description page with placeholders | Required part of the project pages. | The placeholders needs to be replaced with live data in the weeks of integration efforts to handle movie details.
|  | 19:00 | 20:00 | 1 | Weekly Team meeting 2 | Discussed progress on tasks assigned and also discussed parts to be completed during weekend such as parts in front-end and back-end. | Need to work on items assigned in the front-end space. This is to ensure that we stay on track for integration.
Saturday | 2025-05-03 | 11:00 | 17:00 | 6 | Setup the Settings page with Placeholder data. | Required part of the project pages. | The placeholders needs to be replaced with live data in the weeks of integration efforts to handle user specific information.
|  | 17:00 | 19:00 | 2 | Review this week's lecture | The lecture was based on testing of the project | Need to apply this in development for unit testing and to keep in mind items discussed regarding BlackBox testing for testing
Sunday | 2025-05-04 | 15:00 | 18:00 | 3 | Create dialog box to post and view reviews | This component is part of the movie details page of the project. | The placeholders needs to be replaced with live data in the weeks of integration efforts to display reviews and to post reviews provided by users.
|  |  | Total | 31