## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1900315 | Emmanuel Philipose Antony | Week starting: | 2025-05-05
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-05-05 | 19:00 | 20:00 | 1 | Weekly Team meeting 1 | The meeting was to discuss tasks for this week, discuss Milestone 1 Report submission, and record questions to client in the upcoming team meeting. | Milestone 1 report requirements were discussed. Need to work on tasks assigned for this week.
Tuesday | 2025-05-06 | 19:00 | 23:00 | 4 | Learn about Next.JS direct integration | This learning was done to go in line with the discussion of getting movie details directly by Next JS without depending on MongoDB to store movie information as it had storage limitations | Learned the ability of Next.Js to interact directly with external APIs. This is to be used to integrate Movie details page with TMDB APIs.
Wednesday | 2025-05-07 | 19:30 | 23:00 | 3.5 | Research TMDB API methods - 1 | This is to research the methods available for integration to populate the Movie Details page | Listed the necessary APIs for Movie Details page to be used to perform integration.
Thursday | 2025-05-08 | 13:00 | 14:00 | 1 | Weekly Client Meeting with Dr.Li | This meeting was to demostrate the project progress and discuss Milestone 1 report. | Dr. Li provided valuable advise pertaining to the Milestone 1 report.
|  | 15:00 | 18:30 | 3.5 | Research TMDB API methods - 2 | This is to research the methods available for integration to populate the Movie Details page | Listed the necessary APIs for Movie Details page to be used to perform integration.
Friday | 2025-05-09 | 12:00 | 18:00 | 6 | Implement User Profile page with placeholders | Required part of the project pages. | The placeholders needs to be replaced with live data in the weeks of integration efforts to handle user profile information and overview of logged in user.
|  | 19:00 | 20:00 | 1 | Weekly Team meeting 2 | Discussed progress on tasks assigned and also discussed parts to be completed during weekend for Milestone 1 report. | Need to work on items assigned in the front-end space. Also work on the split contribution to Milestone 1 report.
Saturday | 2025-05-10 | 10:30 | 12:30 | 2 | Write the part for Milestone 1 report. | This is required for submission of Milestone 1 report of the team. | Milestone 1 report part of contribution completed.
|  | 2:45 | 20:00 | 5.25 | Create Server Actions for populating various parts in Movie Details Page | Server Actions are required for live data population of the Movie Details page pertaining to each movie | Server Actions for different parts/components of Movie Details page ready for integration.
Sunday | 2025-05-11 | 12:00 | 17:00 | 5 | Integrate the Movie Details page with the Server Actions created. | This is required for live data population of the Movie Details page pertaining to each movie | Movie details components receiving data from TMDB database fully integrated.
|  |  | Total | 32.25