## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1903146 | Silin Ren | Week starting: | 2025-05-19
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-05-19 | 8:30 | 12:30 | 4 | Synchronized backend password requirements with frontend validation rules | Ensures consistency in user registration and improves UX/security alignment | Password rules unified
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly task review and progress alignment | Updated task assignments
Tuesday | 2025-05-20 | 9:00 | 13:00 | 4 | Updated current user review model structure | Supports better data structure for storing user feedback; essential for movie reviews | New model live; supports integration with UI review component
Wednesday | 2025-05-21 | 9:00 | 12:00 | 3 | Implemented bio update feature in user profile | Expands user customization and profile flexibility | Expands user customization and profile flexibility
|  | 13:30 | 17:30 | 4 | Fixed HTTP method from PUT to PATCH in /users/me endpoint | Ensures proper RESTful API practices and avoids client update errors | Endpoint corrected; compatible with frontend logic
Thursday | 2025-05-22 | 13:00 | 14:00 | 1 | Attended client meeting | Aligns project direction with stakeholder expectations; | Gathered feedback on Integration
|  | 13:00 | 17:00 | 4 | Changed rating format from float to int; enforced range 0–10 | Prevents data inconsistency; aligns backend with rating logic expected by frontend | Rating validation passed; synced with database and frontend
Friday | 2025-05-23 | 9:30 | 12:30 | 3 | Added user activity logging (e.g., review, rating actions) | Prepares for user profile page | Activities captured in user records; ready for testing
|  | 11:00 | 12:00 | 1 | Attend Lecture | Understand the importance of Ethics in Software | Improved understanding of Ethics in Software filed
|  | 13:30 | 17:30 | 4 | Final testing for new features | Ensures latest features are test-ready | Pushed to GitHub; ready for code review
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly summary and next plan | Next tasks assigned
|  |  | Total | 30