## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1903146 | Silin Ren | Week starting: | 2025-05-26
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-05-26 | 9:30 | 13:30 | 4 | Completed mobile adaptation of the home page | Improves mobile user experience; ensures responsiveness across devices | Layout adjusted; tested on multiple viewports
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly task review and progress alignment | Updated task assignments
Tuesday | 2025-05-27 | 9:00 | 13:00 | 4 | Completed mobile adaptation of the discover page | Aligns with project’s UX goals for mobile-first users | Discover page now responsive; integrated with search and filter logic
Wednesday | 2025-05-28 | 9:00 | 14:00 | 5 | Optimized discover page design (e.g., layout structure, spacing, font adjustments) | Enhances visual clarity and user navigation | Page updated; UI feedback gathered from team
Thursday | 2025-05-29 | 13:00 | 14:00 | 1 | Attended client meeting | Received feedback on design and mobile usage; confirmed avatar and layout expectations | Follow-up needed: finalize pages based on feedback
|  | 14:00 | 20:00 | 6 | Completed mobile adaptation of the user profile page | Supports mobile usability of user-specific features (bio, avatar, edit function) | Profile page fully responsive; to be refined with data
Friday | 2025-05-30 | 9:30 | 12:30 | 3 | Updated avatar field: added hint “Upload your online avatar” + field accepts URL input | Improves usability; aligns form instructions with backend field expectations | Field updated in form schema and UI
|  | 11:00 | 12:00 | 1 | Attend Lecture | Understand demo and report | Improved understanding of delivery standards
|  | 13:30 | 17:30 | 4 | UI testing and mobile layout verification on all pages | Ensures final compatibility and responsiveness for submission and client demo | All responsive layouts verified
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly summary and next plan | Next tasks assigned
|  |  | Total | 30