## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1903146 | Silin Ren | Week starting: | 2025-05-12
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-05-12 | 9:30 | 12:30 | 3 | Updated user profile API to return watchlists and reviews | Supports frontend display of user-specific data; crucial for settings/profile pages | API now returns complete user info; ready for UI integration
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly task review and progress alignment | Updated task assignments
Tuesday | 2025-05-13 | 9:00 | 13:00 | 4 | Worked on frontend-backend integration and endpoint connection | Enables real-time data flow between frontend UI and backend services | Integrated user data display in user profile page
Wednesday | 2025-05-14 | 9:30 | 12:00 | 2.5 | Updated README.md with MongoDB usage instructions | Improves project documentation | Pushed to repo; improves clarity for DB setup
|  | 14:00 | 18:30 | 4.5 | Worked on frontend-backend integration and endpoint connection | Enables real-time data flow between frontend UI and backend services | Integrated user data display in login page
Thursday | 2025-05-15 | 13:00 | 14:00 | 1 | Attended client meeting | Aligns project direction with stakeholder expectations; | Gathered feedback on UI changes and auth behavior
|  | 14:00 | 20:00 | 6 | Fixed login logic in auth.py (username/password validation logic) | Essential to user access control; prevents login failure and enables secure auth | Functionally verified; user errors now handled correctly
Friday | 2025-05-16 | 9:30 | 12:30 | 3 | Added refresh_token handling in /token route of auth.py | Supports JWT-based session renewal and security extension | Refresh token logic added and tested with Swagger UI
|  | 13:30 | 17:30 | 4 | Implemented avatar upload/delete feature and default avatar setup | Enhances user profile page; adds personalization and user asset management | Avatars stored and rendered; integrated with profile API
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly summary and next plan | Next tasks assigned
|  |  | Total | 30