## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1903146 | Silin Ren | Week starting: | 2025-04-07
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-04-07 | 9:00 | 12:00 | 3 | Write TMDB import script (Day 1) | Enable collection of movie data | Script initialized, basic movie fetching done
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly task review and progress alignment | Updated task assignments
Tuesday | 2025-04-08 | 9:00 | 12:00 | 3 | Write TMDB import script (Day 2) | Expand script to fetch detailed movie data | Added genre and rating fetching logic
|  | 13:00 | 14:00 | 1 | Client Meeting | Client progress review and feedback | Refined requirements based on feedback
|  | 14:00 | 17:00 | 3 | Write TMDB import script (Day 3) | Finalize script and prepare for testing | Data fetching script ready
Wednesday | 2025-04-02 | 9:00 | 12:00 | 3 | Check TMDB import results | Validate and clean imported data | Initial validation and cleaning completed
|  | 14:00 | 17:00 | 3 | Check TMDB import results | Continue validating, prepare for backend usage | Data finalized for serving
Thursday | 2025-04-03 | 9:00 | 11:00 | 2 | Implement data return API | Backend provides real movie data to frontend | Basic movie API endpoints implemented
|  | 13:30 | 16:30 | 3 | Implement data return API | Extend movie API endpoints, add search, detail endpoints | API finalized and tested
Friday | 2025-04-04 | 9:00 | 11:00 | 2 | Add login verification | Setup basic login authentication | User authentication module initialized
|  | 11:00 | 12:00 | 1 | Attend Lecture | Understand User Interfaces | Improved understanding of delivery standards
|  | 13:30 | 17:30 | 4 | Add login verification | Secure backend endpoints | Backend protected with authentication
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly summary and next sprint planning | Next tasks assigned
|  |  | Total | 30