## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1903146 | Silin Ren | Week starting: | 2025-06-02
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-06-02 | 9:30 | 13:30 | 4 | Completed mobile adaptation of the watchlist page | Enables users to manage watchlists effectively across mobile devices | Responsive design implemented and visually tested
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly task review and progress alignment | Updated tasks
Tuesday | 2025-06-03 | 9:00 | 13:00 | 4 | Completed mobile adaptation of the Movie Description page | Supports mobile usability of movies description features | Page fully responsive
Wednesday | 2025-06-04 | 9:00 | 12:30 | 3.5 | Completed mobile adaptation of the "Post a review" section on MovieDesc page | Ensures core feature (user-generated reviews) is accessible and usable on mobile | Mobile review interface completed; UI tested with user input
Thursday | 2025-06-05 | 9:00 | 12:00 | 3 | Prepared content and visuals for the presentation slides | Prepares for client and academic evaluation; shows project value and workflow | Slide outline completed; awaiting team review
Friday | 2025-06-06 | 9:00 | 11:00 | 2 | Adjusted presentation slides | Supports final milestone delivery and presentation success | Awaiting team review
|  | 11:00 | 12:00 | 1 | Attended Lecture | Understand the final presentation | Improved understanding of delivery standards
|  | 15:00 | 16:00 | 1 | Attended client meeting | Collected feedback for final presentation slides | Follow-up needed: finalize slides based on feedback
|  | 16:00 | 17:00 | 1 | Group Meeting | Weekly summary and next plan | Final tasks assigned
Saturday | 2025-06-07 | 9:00 | 13:00 | 4 | Adjusted presentation slides | Supports final milestone delivery and presentation success | Discussing with team
Sunday | 2025-06-08 | 12:00 | 19:00 | 7 | Finalized presentation slides and assigned personal parts for team | Supports final presentation success | Demo on next Tuesday
|  |  | Total | 31.5