## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1903146 | Silin Ren | Week starting: | 2025-03-10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-03-10 | 9:00 | 14:00 | 5 | Coordinated and organized the client meeting and team meeting. | Established initial project communication. | Clarified client requirements. Assigned team roles for meeting agenda and minutes rotation.
Tuesday | 2025-03-11 | 13:30 | 17:30 | 4 | Familiar with Git and Github. | Essential for managing project versions and collaboration. | Successfully set up the repository and uploaded initial documentation.
Wednesday | 2025-03-12 | 8:00 | 15:00 | 7 | Conducted research on API integration. | Required for movie data retrieval. | Identified potential APIs (TMDB, OMDB) and analyzed data availability. Next step: Define API usage plan.
Thursday | 2025-03-13 | 9:00 | 13:00 | 4 | Learned React framework. | Required for front-end development. | Explored component-based architecture and state management.
|  | 14:00 | 15:00 | 1 | Attended Workshop | Covered assessment requirements and project pitching. | Improved understanding of pitch presentation skills. Next: Apply learnings to Pitch preparation.
Friday | 2025-03-14 | 11:00 | 13:00 | 2 | Attended lecture. | Focused on requirement decomposition. | Gained knowledge of breaking down large requirements into manageable tasks. Next: Apply this to our project scope.
|  | 19:00 | 20:00 | 1 | Team meeting. | Reviewed project scope and divided upcoming tasks. | Defined next steps for API research and technology selection.
Saturday | 2025-03-15 | 9:00 | 12:00 | 3 | Conducted research on back-end technologies. | Needed for API implementation and database setup. | Evaluated options (Node.js, FastAPI). Next: Confirm back-end tech stack.
Sunday | 2025-03-16 | 19:00 | 22:00 | 3 | Casual team meeting. | Focused on project management and user stories. | Defined key User Stories and explored GitHub for Agile development management.
|  |  | Total | 30