## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1903146 | Silin Ren | Week starting: | 2025-05-05
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-05-05 | 10:00 | 18:00 | 8 | Worked on movie description data mapping; provided TMDB data response samples | Backend support for dynamic movie detail page development | Shared backend response samples; supported frontend development
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly task review and progress alignment | Updated task assignments
Tuesday | 2025-05-06 | 9:00 | 5:00 | 8 | Developed JWT-based login and registration APIs; began integrating error handling for authentication | Enables secure login and token-based authorization for user-specific interactions | Auth system working; need to implement distinct error messages
Wednesday | 2025-05-07 | 10:00 | 13:00 | 3 | Finalized backend user review structure; discussed user record schema and field plan | Supports user profile, review history, and frontend-user data mapping | User model schema drafted; awaiting front-end field confirmation
Thursday | 2025-05-08 | 12:00 | 16:00 | 4 | Attended client meeting; collected feedback on sorting, login UI, chatbot confirmation | Client validation of current system; redirected design priorities | Feedback logged; prepared to discuss in internal group meeting
Friday | 2025-05-02 | 9:30 | 16:30 | 7 | Worked on backend database structure for user profile; planned integration strategy with frontend | Separates authentication and profile logic; enables dynamic settings & reviews pages | Backend schema finalized; integrating with frontend via API
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly summary and next sprint planning | Next tasks assigned
|  |  | Total | 32