## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1900315 | Emmanuel Philipose Antony | Week starting: | 2025-03-10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-03-10 | 19:00 | 20:00 | 1 | Team meeting | Introduction meeting for team members | Got understanding of the coding background and fields each team member is comfortable in.
Tuesday | 2025-03-11 | 16:00 | 23:00 | 7 | Learn React | This is a potential front end framework that can be used | The learning outcome gave a strong sense of react's capabilities and that the framework will be a good fit for the project
Wednesday | 2025-03-12 | 19:00 | 23:00 | 4 | Investigate Back-End options with Python | Search for potential back end framework that can be used | The investigation gave out FastAPI and Django as few options available. But FastAPI's capabilites made it a stronger option to be applied in this project
Thursday | 2025-03-13 | 17:00 | 21:00 | 4 | Investigate Database options fitting use case | Search for potential database that can be used that can process requirements such as encrypted authentication, movie description data, etc | The investigation gave out MongoDB and MySQL as options available. MongoDB being a cloud database, NoSQL option and able to handle any kind of data made it a strongest to be applied in this project
|  | 21:00 | 23:00 | 2 | Investigate movie database options | Movie data from an external source is vital to the representation of movies in homepage. | OMDB and TMDB came up as potential options to be integrated. To be researched further.
Friday | 2025-03-14 | 19:00 | 20:00 | 1 | Team meeting | Discussed project scope and upcoming tasks for the project | This meeting helped decide the tech stack and movie API to be selected.
|  | 20:00 | 22:00 | 2 | Review lecture content online | The lecture focused on requirements and its elements | Helped understand splitting of requirements into tasks and how to apply this to our project
Saturday | 2025-03-15 | 12:00 | 19:00 | 7 | Learn Fast API | This is a potential back end framework that can be used | The team meeting consensus was to use FastAPI as backend. This learning helped understand the inbuilt capabilities of FastAPI
Sunday | 2025-03-16 | 19:00 | 22:00 | 3 | Additional Team meeting | This meeting was to create a user story split for the project to aid project management | This team meeting helped identify and finalise the key user stories and the usage of Github for effective agile project management
|  |  | Total | 31