## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1900315 | Emmanuel Philipose Antony | Week starting: | 2025-03-17
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-03-17 | 19:00 | 20:00 | 1 | Weekly Team meeting 1 | The meeting was to discuss tasks for this week and discuss requirements for prototype | The prototype requirements were decided. Another piece of discussion was to make a few refinements to the finalised user stories. Teammates work on the tasks assigned as per meeting discussion
Tuesday | 2025-03-18 | 13:00 | 14:00 | 1 | Weekly Client Meeting with Dr.Li | The meeting's main discussion was clarity on requirements decided and how it fits with the end goal. | Dr.Li provided valuable feedback on the requirements. Need to keep that in mind for further development tasks
Wednesday | 2025-03-19 | 20:00 | 22:00 | 2 | Research on setting up Front End Environment | This research is needed to set up the front-end part with the dependencies of Tech stack decided | The research yielded outcome of how to set up front-end. Create-react-app was depricated and hence Next JS was decided as the best framework from the alternatives provided in the documentation
Thursday | 2025-03-20 | 19:00 | 21:00 | 2 | Research on setting up Back End Environment | This research is needed to set up the back-end part with the dependencies of Tech stack decided | The research yielded outcome of how to set up back-end with FastAPI and also the need for python venv.
|  | 21:00 | 23:00 | 2 | Research on setting up Database in the Back-End Environment | This research is needed to set up the database part with the dependencies of Tech stack decided | The research yielded outcome of how to set up database with MongoDB connection module pymongo.
Friday | 2025-03-21 | 14:00 | 19:00 | 5 | Setup Front-End Environment with Next JS and Material UI components | This setup is done as per research done on front-end environment setup for Next JS and added Material UI components to it. | Successfully set up front end environment with Next JS and Material UI components.
|  | 19:00 | 20:00 | 1 | Weekly Team meeting 2 | Discussed progress on tasks assigned and also discussed parts to be completed during weekend | Initiated the creation of a quick catchup during the weekend to discuss environment setup progress
|  | 20:00 | 23:00 | 3 | Prepare instructions for teammates to install front-end components and how to use them from Git in Readme.md in the Frontend branch | Instructions are vital for the teammates to pull Frontend branch and set it up ready for development. | The instructions were created and then uploaded to github Frontend branch in Readme.md
Saturday | 2025-03-22 | 9:00 | 14:00 | 5 | Setup Back-End Environment with FastAPI and Python venv | This setup is done as per research done on back-end environment setup for FastAPI and added Python venv to it. | Successfully set up back end environment with FastAPI and Python venv.
|  | 14:00 | 19:00 | 5 | Setup MongoDB Database and ensure connection with Back-End | This setup is done as per research done on database setup for MongoDB and added Pymongo module to connect to back-end. | Successfully set up database environment with MongoDB and Pymongo module and tested connection.
|  | 19:00 | 22:00 | 3 | Prepare instructions for teammates to install back-end components and how to use them from Git in Readme.md in the Backend branch | Instructions are vital for the teammates to pull Backend branch and set it up ready for development. | The instructions were created and then uploaded to github Backend branch in Readme.md
Sunday | 2025-03-23 | 11:00 | 13:00 | 2 | Review this week's lecture online | The lecture focused on Project management | Have to discuss in next team meeting how to apply steps mentioned in lecture to project
|  |  | Total | 32