## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1903146 | Silin Ren | Week starting: | 2025-04-28
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-04-28 | 9:30 | 17:30 | 8 | Refactored backend structure; implemented rating & comment APIs (POST/PUT/DELETE) | Core interaction module; enables user reviews and engagement | Basic API functions completed; plan to integrate user authentication for access control
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly task review and progress alignment | Updated task assignments
Tuesday | 2025-04-29 | 10:00 | 18:00 | 8 | Designed and implemented JWT-based registration/login API; tested frontend-backend token flow | Enables secure user authentication, supports user-specific features | Auth system completed with JWT issuance and validation
Wednesday | 2025-04-30 | 9:00 | 12:00 | 3 | Mapped TMDB data structure and clarified backend movie detail response format | Supports movie detail page by providing structured data like cast, director, and budget | Format finalized; backend ready to deliver movie details
Thursday | 2025-05-01 | 13:30 | 17:30 | 4 | Attended client meeting; documented feedback; reviewed technical priorities | Aligns project direction with stakeholder expectations; confirmed chatbot and UI direction | Feedback translated into updated dev plan; prioritize search page and UI polishing
Friday | 2025-05-02 | 9:30 | 16:30 | 7 | Proposed user data schema; supported frontend testing for JWT decoding | Ensures database design supports profile page and review linkage | Data schema drafted; frontend successfully integrated JWT info
|  | 11:00 | 12:00 | 1 | Attend Lecture | Understand Testing Plan | Improved understanding of delivery standards
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly summary and next sprint planning | Next tasks assigned
|  |  | Total | 33