## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1903146 | Silin Ren | Week starting: | 2025-03-17
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-03-17 | 19:00 | 20:00 | 1 | Participated team meeting. | Required for initial prototype development and refining user stories. | Clarified additional prototype requirements. Gathered feedback to refine user stories. Next: Update documentation & finalize user stories.
|  | 12:00 | 18:00 | 6 | Conducted research on backend technology. | Needed for API implementation and database setup. | Next: Select the backend stack.
Tuesday | 2025-03-18 | 14:00 | 15:00 | 1 | Participated client meeting with Dr. Li. | Focused on reporting progress and ensuring alignment with project goals. | Received feedback on the current work. Next: Assign new tasks to the team based on client input.
|  | 22:00 | 0:00 | 2 | Assigned tasks to team. | Ensured balanced workload distribution for efficient development. | Divided tasks among team members. Next: Monitor progress & provide support if needed.
Wednesday | 2025-03-19 | 8:00 | 13:00 | 5 | Designed database schema and relationships. | Crucial for storing user, movie, rating, and review data efficiently. | Defined primary entities and relationships. Created initial SQL schema. Next: Trying to implement database in MySQL and test queries.
Thursday | 2025-03-20 | 9:00 | 13:00 | 4 | Tried FastAPI + MySQL | Required for frontend development. | Next: Confirm the backend stack.
Friday | 2025-03-21 | 11:00 | 13:00 | 2 | Attended lecture. | Focused on project management. | Gained knowledge of project management. Next: Apply this to our project management.
|  | 13:00 | 14:00 | 1 | Team meeting. | Reviewed project scope and divided upcoming tasks. | Defined next steps for API research and technology selection.
Saturday | 2025-03-22 | 9:00 | 12:00 | 3 | Discussion and conducted setting up on backend infrastructure. | Needed for API implementation and database setup. | Selected FastAPI+MongoDB. Next: Further development feature.
|  | 14:00 | 20:00 | 6 | Conducted setting up on backend infrastructure.
|  |  | Total | 31