## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1917266 | Daming Chen | Week starting: | 2025-05-12
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-05-12 | 13:00 | 17:00 | 4 | Code Review and organizing and restructuring GitHub Branches. | Enhance code readability and standardize GitHub branch naming for clearer and more explicit meaning. | Next Step: Team Meeting.
|  | 19:00 | 20:00 | 1 | Participated group meeting. | Present current progress and gather feedback. | Next Step: Refine project alignments based on feedback.
Tuesday | 2025-05-13 | 20:00 | 22:00 | 2 | Researching the integration of Next.js and Fast API | Preparing to implement front-end and back-end communication for the project. | Next step: Implement login and registration features.
Wednesday | 2025-05-14 | 19:00 | 20:00 | 1 | Participated small group meeting. | Research, discuss, and try implementing the frontend-backend communication approach. | Next step: Implement login and registration features.
Thursday | 2025-05-15 | 13:00 | 14:00 | 1 | Participated client meeting. | Present current progress and gather feedback. | Next Step: Refine project alignments based on feedback.
|  | 8:00 | 16:00 | 8 | Implemented Auth functionality. | Integrate with the backend server to implement front-end and back-end interaction, achieving user authentication functionality with form validation, error feedback, and high usability. | Next step: Sessions management.
Friday | 2025-05-16 | 19:00 | 20:00 | 1 | Participated group meeting. | Present current progress and gather feedback. | Next Step: Refine project alignments based on feedback.
|  | 20:00 | 2:00 | 6 | Implement session management. | Set up cookie storage, implement session logic compliant with the OAuth 2.0 standard, and manage user tokens using Next.js. | Next step: Discover page
Saturday | 2025-05-17 | 18:00 | 12:00 | 6 | Develop the Discover page. | Implement multiple filters and sorting methods for the advanced search on the Discover page, as well as pagination for the movie list. | Next Step: Refine project alignments based on feedback.
|  |  | Total | 30