## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1815456 | Zixuan Li | Week starting: | 2025-05-26
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-05-26 | 10:00 | 15:30 | 5.5 | Executed completed test cases and marked their status. | Tracks progress and verifies which functionalities are working as expected. | Updated test case sheet with status; will proceed with further testing.
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly task review and progress alignment | Updated task assignments
Tuesday | 2025-05-27 | 20:00 | 0:00 | 4 | Continued executing test cases, including newly added item | Ensures full test coverage and validates critical system components. | Progress recorded; prepare bug log for failed test cases.
Wednesday | 2025-05-28 | 9:00 | 14:00 | 5 | Documented bugs discovered during testing. | Centralizes defect tracking and supports debugging and quality assurance. | Bug log updated; issues assigned for resolution.
Thursday | 2025-05-29 | 13:00 | 14:00 | 1 | Attended client meeting | Received feedback on design and mobile usage; confirmed avatar and layout expectations | Follow-up needed: finalize pages based on feedback
Friday | 2025-05-30 | 9:30 | 12:30 | 3 | Documented bugs discovered during testing. | Centralizes defect tracking and supports debugging and quality assurance. | Bug log updated; issues assigned for resolution.
|  | 11:00 | 12:00 | 1 | Attend Lecture | Understand demo and report | Improved understanding of delivery standards
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly summary and next plan | Next tasks assigned
Saturday | 2025/5/31 | 10:00 | 16:00 | 6 | Drafted the final presentation slides (structure and key content). | Prepares clear communication for project showcase and assessment. | Initial draft completed; ready for team review and refinement.
Sunday | 2025/6/1 | 21:00 | 0:00 | 3 | Continued refining the final presentation draft. | Enhances the clarity, professionalism, and completeness of final presentation. | Visuals and speaking points improved; ready for team walkthrough.
|  |  | Total | 30.5