## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1815456 | Zixuan Li | Week starting: | 2025-06-02
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-06-02 | 10:30 | 16:30 | 6 | Revised the final draft of the presentation slides in preparation for team feedback session. | Prepares the team for presentation review; ensures clarity and completeness of content. | Draft ready for internal review and comments.
|  | 19:00 | 21:00 | 2 | Group Meeting | Weekly task review and progress alignment | Updated tasks
Tuesday | 2025-06-03 | 10:00 | 17:00 | 6 | Refined presentation slides based on team feedback. | Ensures the presentation reflects team consensus and addresses reviewer expectations. | Updated version complete; ready for final polishing.
Wednesday | 2025-06-04 | 9:00 | 15:30 | 6.5 | Finalized presentation slides for submission and delivery. | Ensures delivery material is presentation-ready and aligned with assessment criteria. | Final slide deck completed and approved by team.
Thursday | 2025-06-05 | 10:00 | 15:00 | 5 | Designed and formatted the final PowerPoint presentation. | Translates content into a visual format suitable for formal presentation. | Polished and visually structured slides ready for use.
Friday | 2025-06-06 | 15:00 | 16:00 | 1 | Attended client meeting | Collected feedback for final presentation slides | Follow-up needed: finalize slides based on feedback
|  | 16:00 | 17:00 | 1 | Group Meeting | Weekly summary and next plan | Final tasks assigned
Saturday | 2025-06-07 | 9:30 | 13:30 | 4 | Updated and expanded the presentation slides; added new user scenario. | Enhances presentation impact and aligns with updated user journey. | Scenario content added; visuals updated accordingly.
|  | 14:00 | 15:00 | 3 | Drafted presentation script for final pitch delivery. | Prepares a coherent verbal presentation to accompany slides. | Script completed; ready for rehearsal and feedback.
|  |  | Total | 34.5