## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1815456 | Zixuan Li | Week starting: | 2025-05-05
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-05-05 | 8:00 | 11:00 | 3 | Watched lecture recording on software testing; summarized key takeaways. | Builds foundational understanding of effective testing strategies, crucial for upcoming test plan and implementation. | Compiled summary of testing concepts (e.g., test cases, coverage, E2E testing); apply insights to refine project’s testing approach. | 1
|  | 11:00 | 18:00 | 7 | Modified multiple test-related files and implemented three layers of testing: E2E tests for root and movie endpoints using FastAPI’s test client, Unit test for movie search with patched DB call, Auth service token verification. | Ensures reliability across critical components—API routing, data services, and authentication—by validating expected behaviors through comprehensive testing. | There are bugs with test case. | 1
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly task review and progress alignment | Updated task assignments | 1
Tuesday | 2025-05-06 | 13:00 | 19:00 | 6 | Debugged failing test cases and resolved backend error responses; continued testing for improved stability. | Critical for ensuring robustness and reliability of backend services before integration and deployment. | Plan to rerun full test suite and begin edge case validation.
Wednesday | 2025-05-07 | 20:00 | 1:00 | 5 | Completed E2E test for the authentication feature under valid input conditions. | Verifies that login functionality works correctly under expected use, building confidence in user session management. | Test passed successfully; next step is to test edge cases (e.g., wrong password, expired token).
Thursday | 2025-05-08 | 13:00 | 14:00 | 1 | Attended client meeting; collected feedback on sorting, login UI, chatbot confirmation | Client validation of current system; redirected design priorities | Feedback logged; prepared to discuss in internal group meeting | 1
Friday | 2025-05-09 | 9:30 | 15:30 | 6 | Wrote Milestone 1 Report, including project scope, initial deliverables, achieved outcomes, and team reflections. | Provides a formal checkpoint aligning actual outcomes with the initial plan; essential for tracking progress and guiding future development. | Provides a formal checkpoint aligning actual outcomes with the initial plan; essential for tracking progress and guiding future development.
|  | 22:00 | 2:00 | 4 | Tested user registration and login endpoints, covering both valid and invalid input scenarios. | Essential for validating core authentication flows, ensuring reliable and secure user access. | All major test cases passed; will continue refining coverage by testing edge cases (e.g., duplicate emails, weak passwords).
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly summary and next sprint planning | Next tasks assigned
|  |  | Total | 34