## Sheet2
MCI Project Weekly Time Sheet
Team | NL1C | Student ID |  | a1815456 | Zixuan Li | Week starting: | 2025-05-12
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2025-05-12 | 9:30 | 12:30 | 3 | Refined the test plan again based on updated team submissions. | Refines test plan to align with the latest backend code implementation. | Updated test structure drafted; ready for team feedback and approval.
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly task review and progress alignment | Updated task assignments
Wednesday | 2025-05-14 | 10:30 | 12:30 | 2 | Refined the test plan again based on updated team submissions. | Refines and adjusts the test plan to match final code logic. | Refined draft completed; pending team review.
|  | 14:00 | 18:00 | 4 | Identified and summarized issues in the test plan design for upcoming team discussion. | Identifies critical issues in testing design to improve accuracy and coverage. | Problems documented; discussion scheduled for resolution and test revision.
Thursday | 2025-05-15 | 13:00 | 14:00 | 1 | Attended client meeting | Aligns project direction with stakeholder expectations; | Gathered feedback on UI changes and auth behavior
|  | 14:00 | 20:00 | 6 | Collected client feedback and explored black-box testing; studied its methodology and application. | Converts client feedback into actionable test items using black-box methods. | Initial test cases created; ready for internal validation.
Friday | 2025-05-16 | 13:00 | 19:00 | 6 | Drafted initial test plan using black-box test case templates. | Ensures test planning structure supports systematic QA process. | Draft to be reviewed by team for completeness and correctness.
|  | 19:00 | 20:00 | 1 | Group Meeting | Weekly summary and next plan | Next tasks assigned
Saturday | 2025-05-17 | 10:00 | 18:00 | 6 | Continued editing and refining the test plan. | Ensures continuous refinement of test plan for improved project quality control. | Intermediate test plan version completed; team review next.
|  |  | Total | 30